## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | 2 | Works, login page displays -EW |  | KC 4/3
As a Admin I want to be able to manages which needs are currently needed: Create/ Delete/Change Quantity Needed | Given that I am on the Needs page I create create, delete, and change the quantity needed for needs. | 2 | Works, .json updated by UI interactions -EW |  | KC 4/3 Cost should display %.2f ( the 2 decimals)
As a helper, if there are no needs currently wanted, I will see a message that tells me as such. | Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | 2 | Sort of works? If no needs are present then none are visible, implicitly showing that there are none. Works assuming Users can pick up on context clues. -EW |  | Kc 4/3 No 'special' message
As a Admin I want to be able to change the information of each need such as the location, description, and priority | Given that I am on the needs page with needs present I want to be able to edit the description and quantity of each of the needs. | 2 | Works, .json updated by UI interactions -EW |  | KC 4/3
As a helper, if needs are available to contribute, I would like to be able to add them to my basket. | Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | 2 | Works, UI has buttons to move needs into basket, which also update the page to show the new basket with the needs in it -EW |  | KC 4/3
As a helper, if I have added needs to my basket I would like to be able to purchase them. | Given that I am in my basket when there are needs in my basket I would like to purchase them. | 2 | Works, UI has purchase button that removes from basket, updates quantity in cupboard, and deletes if necessary. -EW |  | KC 4/3
As a HELPER, I want TO SEE RECEIPTS OF MY PURCHASES, so I CAN KNOW WHAT I BOUGHT, WHEN I BOUGHT IT, AND FOR HOW MUCH //IN PROGRESS ON DIFFERENT BRANCH | Given that I have made a purchase, I would like a receipt to popup with the total, the items included, and the date + time | 3 |  |  | not ready yet
As a HELPER, I want to PURCHASE ALL MY NEEDS AT ONCE to SAVE TIME. | Given that I hit the "purchase all" button, all needs should be purchased at once. | 3 |  |  | KC 4/3 , user should know when a purchase has failed
As a helper, I want to be able to purchase more than one of a need at a time, to save MY time | Given that I adjust a quantity slider in the UI, the quantity of a need in my basket should increase/decrease. If my quantity exceeds the amount available, only what is available should be purchased | 3 |  |  | KC 4/3
As an ADMIN, I want TO GROUP NEEDS BY ASSOCIATED DISASTER, so HELPERS CAN HELP WITH CAUSES THEY CARE ABOUT //IN PROGRESS ON DIFFERENT BRANCH | Given that I create a disaster, I should be able to add needs to it for helpers to see. Given that a helper searches for a disaster, they should see relevant results, and be able to purchase needs directly from it | 3 |  |  | Not ready yet
checkout deleted need
Checking out a deleted need doesn't brick the application, but the user is not informed that the checkout did not find anything. Looks the exact same as a success.
All baskets should not be fetched whenever we get our own basket